## Indicative PP Format
Format for submission of Indicative Annual procurement plan [STRIVE]
Name of State : Telangana
Annual Procurement Plan for Financial Year : 2023-2024
Date of Approval of Annual Procurement Plan :
Approved By/Name of Approving Authority : SPIU Telangana
S. No. | Procurement Category | Full Name of Procuring Entity (SPIU/ ITI/ SMAC/ IC) | Name/Description of Procurement/Selection | Estimated Cost [INR] | Results Area | Procurement Mode | Applicable Procurement Rules | Use of GEM [Yes/No] | Use of eProcurement [Yes/No] | Procurement Method | Market Approach [National/ International] | Proposed Procurement Start Date | Pre-bid Conference Date [if any] | Proposed Procurement End Date | Tentative Contract Award Date | Tentative Contract Duration [Months] | Tentative Completion Date | Remarks
Date [if any]
[1] | [2] | [3] | [4] | [5] | [6] | [7] | [8] | [9] | [10] | [11] | [12] | [13] | [14] | [15] | [16] | [17] | [18] | [19]
1 | SCHEDULES | IMC of GOVT. ITI ALER | Machinery,Equipments,Tools, Furniture, etc., | 2944715.96 exculsing GST | RA2 | e-procurment | - | No | Yes | open tender No. 411476, | National | - | - | - | - | - | - | IOT [Smart city]
| BOOKS |  |  | 22080 | RA2 | e-procurment | - | No | Yes | online | National | - | - | - | - | - | - | IOT [Smart city]
2 | BOOKS | IMC OF GOVT ITI KALWAKURTHY | TOOLS MACHINERY AND EQUIPMENTS | 2489798 | RA1 | E PROCURE /GEM | AS PER PROCEDURE | YES | YES | E PROCURE /GEM | National | 25.02.2024 | 15.03.2024 | 15.05.2024 | 15.03.2024 | 3 | 30.05.2024
3 | Schedules | IMC of Govt.ITI, Karimnagar | Tools, Equipment, Machinery & Furniture | 2400000 | RA 01 | eProcurement | Yes | No | Yes | Open tender notification | National | 07.8.2023 | 2023-07-25 | 21.09.2023 | 23.09.2023 | 45 days | 29.09.2023 | IOT & MAEE
4 | Schedules | IMC of Govt.ITI, Khammam | Tools, Equipment, Machinery & Furniture | 40,000,00.00 | RA 01 | eProcurement | Yes | No | Yes | Open tender notification | National | 23.8.2023 | 2023-09-14 | 29.09.2023 | 10.10.2023 | 45 days | 16.12.2023 | Solar Technician
5 | Schedule - 01 | Govt. ITI Mancherial | Tools, Equipment, Machinery & Furniture (Hand Tools) |  | RA 2 | GEM PORTAL | 1) GEM/2023/B/3868952 Dt:24-08-2023 for Rs: 3,87,907/- (Hand Tools ) | Yes | No | GEM Open BID | National | [6 empty] | Received Good and Material , payment not Done
| Schedule - 02 |  | Tools, Equipment, Machinery & Furniture(Solar Core Practical Equipment-I) |  | RA 2 | GEM PORTAL | 2) GEM/2023/B/3868253 Dt:24-08-2023 for Rs: 11,78,997/- (Core Solar Practical Equipment ) | Yes | No | GEM Open BID | National | [6 empty] | Bid Awarded to Multi Tech systems Hyderabad,Received Good and Material , payment not Done
| Schedule - 03 |  | Tools, Equipment, Machinery & Furniture(Solar Core Practical Equipment-II) |  | RA 2 | GEM PORTAL | 3)GEM/2023/B/3923985 Dt:06-09-2023 for Rs: 16,30,758 /- (Core Solar Practical Equipment ) | Yes | No | GEM Open BID | National | [6 empty] | Bid Awarded to Multi Tech systems Hyderabad,Received Good and Material , payment not Done
| Schedule - 04 |  | Tools, Equipment, Machinery & Furniture (Saftey hazard Equipment) |  | RA 2 | GEM PORTAL | 4)GEM/2023/B/3924282 Dt:06-09-2023 for Rs: 20,190/- (Saftey hazard& Equipment ) | Yes | No | GEM Open BID | National | [6 empty] | Received Good and Material , payment not Done
| Schedule - 05 |  | Tools, Equipment, Machinery & Furniture ( Class Room Furniture) |  | RA 2 | GEM PORTAL | 5)GEM/2023/B/3903630 Dt:01-09-2023 for Rs: 3,53,960/- (Classroom Furniture ) | Yes | No | GEM Open BID | National | [6 empty] | Received Good and Material , payment not Done
6 | Schedules | IMC of Govt ITI Musheerabad | Machinery,Equipment, Tools, Furniture etc | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
7 | Procurement of Tools and Equipment's | IMC OF GOVT ITI (Girls) Nizamabad | Machinery,Equipment, Tools, Furniture etc | 2974921 | RA1 | Purchase of Tools,Equipment's | Yes | Yes | Yes | Purchase of Tools,and Equipment's | National | Yes | 2023-07-20 | Yes | Yes | Yes | Yes
8 | Schedules | IMC DLTC ITI VIKARABAD | Machinery,Equipment, Tools, Furniture etc | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
9 | Schedules | IMC of Govt ITI Alwal | Machinery,Equipment, Tools, Furniture etc | 1594926 | RA1 | eProcurement | Yes | No | Yes | Open Tender Notification | National | 2023-05-26 | 2023-06-02 | - | - | - | - | Solar Technician(EL) trade Procurement of Tools Machinery and Equipment work is under process
10 | Schedules | IMC ITI SANGAREDDY | NIL | NIL | NIL | NIL | yes | No | Yes | NIL | National | NIL | NIL | NIL | NIL | NIL | NIL
Annual Procurement Plan may be prepared on the assumption that total budget will be released
Procuring entities shall ensure that procurements are carried out as per Delegation of Financial Powers and within Categories defined as 'Eligible Expenditure' in the Operations Manual
Specifications for goods to be procured shall be as per approved specifications for that trade, approved by the Competent Authority

## Notes
S No. | Indicative Procurement Category | Results Area
1 | Goods | RA 1
2 | Services | RA 2
3 | Misc (Please Specify) | RA 4
Use of GEM
Yes
No
Name/Description of Procurement/Selection
Details of category eg. Furniture, equipment, etc.
Market Approach
National
International